## Sprint 1
Restaurant Booking System - Sprint 1 Execution
User Story ID | User Story | Ticket ID | Ticket Title / Description | Priority | Start Date | End Date | Story Points | Resource
US-01 | Customer Registration | T-01 | Design and implement registration | High | 1-Jul | 3-Jul | 5 | 2
US-02 | Customer Login | T-02 | Design and implement login | High | 4-Jul | 5-Jul | 3 | 2
US-03 | Search Restaurants | T-03 | Design and implement restaurant search | High | 8-Jul | 9-Jul | 5 | 2
US-04 | View Restaurant Details | T-04 | Create restaurant details view | High | 10-Jul | 12-Jul | 3 | 3
US-05 | View Table Availability | T-05 | Implement table/time availability | High | 15-Jul | 18-Jul | 5 | 3
US-06 | Make Reservation | T-06 | Implement reservation workflow | High | 22-Jul | 24-Jul | 8 | 3