## Sprint 2
Restaurant Booking System - Sprint 2 Execution
User Story ID | User Story | Ticket ID | Ticket Title / Description | Priority | Start Date | End Date | Story Points | Resource
US-07 | View My Reservations | T-07 | Design reservation list | Medium | 25-Jul | 26-Jul | 3 | 3
US-08 | Cancel Reservation | T-08 | Implement reservation cancellation | Medium | 29-Jul | 31-Jul | 3 | 3
US-09 | Modify Reservation | T-09 | Implement reservation modification | Medium | 1-Aug | 2-Aug | 5 | 3
US-10 | Manage Tables | T-10 | Implement table management | Medium | 5-Aug | 9-Aug | 5 | 3
US-11 | Manage Reservations | T-11 | Implement staff reservation management | Medium | 12-Aug | 16-Aug | 5 | 2
US-12 | Manage Restaurant Schedule | T-12 | Implement schedule management | Medium | 19-Aug | 20-Aug | 5 | 2
US-13 | User Logout | T-13 | Implement secure logout | Medium | 21-Aug | 23-Aug | 2 | 2